## Slide 1
BCG-STYLE
04 / EXECUTION
Initiative Prioritizer — Apex HR
Apex HR
2026-06-18
Powered by The Consultant's Guide to Claude · 21 BCG-Style Skills

## Slide 2
EXECUTIVE SUMMARY
Initiative List
→
Payroll partner integration (Check API)
→
Native payroll build
→
Analytics monetization (unbundle from core)
→
APAC market entry
Apex HR
BCG Consulting Framework · Apex HR · 2026-06-18
2 / 5

## Slide 3
Priority Matrix
Apex HR
Initiative
Strategic Impact
Feasibility
Dependencies
Effort
Priority
Win/loss analysis
High (validates everything)
Very High
None
Low
#1 — Do now (Week 1)
Payroll partner (Check)
Very High
High
Win/loss result
Medium
#2 — Start Q3 2026
Analytics monetization
High
High
Pricing rework
Low
#3 — Start Q3 2026
SMB floor pricing
Medium
Very High
Sales alignment
Low
#4 — Start Q3 2026
Customer advisory board
Medium
High
Payroll roadmap
Low
#5 — Start Q3 2026
Native payroll build
Very High
Medium
Partner live + ARR
Very High
#6 — Start Q1 2027
Upmarket (500–1,000)
Medium
Medium
Product features
High
#7 — Q2 2027
APAC entry
Medium
Low
Payroll live + compliance
Very High
#8 — Q3 2027+
BCG Consulting Framework · Apex HR · 2026-06-18
3 / 5

## Slide 4
Quick Wins (Start Immediately)
Apex HR
Win/loss analysis — 4 weeks, no budget, validates entire strategy
Analytics unbundling — 6 weeks, no engineering, immediate ARR upside
SMB floor pricing — sales policy change, instant margin improvement
BCG Consulting Framework · Apex HR · 2026-06-18
4 / 5

## Slide 5
Kill / Defer List
Apex HR
APAC: defer minimum 18 months; resources needed for payroll
Native payroll build: don't start until partner is live and generating revenue to fund it
BCG Consulting Framework · Apex HR · 2026-06-18
5 / 5