## Slide 1
BCG-STYLE
06 / EXECUTIVE COMMS
Stakeholder Alignment — Apex HR Payroll Strategy
Apex HR
2026-06-18
Powered by The Consultant's Guide to Claude · 21 BCG-Style Skills

## Slide 2
EXECUTIVE SUMMARY
Strategy Requiring Alignment
Build payroll via Check partnership (9 months, $800K), defer APAC, re-focus GTM on 150–300 employee segment. Requires Board approval for spend + CTO/CPO commitment.
Apex HR
BCG Consulting Framework · Apex HR · 2026-06-18
2 / 5

## Slide 3
Stakeholder Map
Apex HR
Stakeholder
Role
Disposition
Decision Criteria
Primary Concern
CEO
Sponsor + Decision Maker
Supportive
Growth trajectory credibility
Will this actually recover win r…
Board / Lead Investor
Approves capital allocation
Neutral
ROI, timeline, competitive logic
Is $800K the right bet vs. other…
CTO
Builds the payroll engine
Cautiously supportive
Technical feasibility of Check i…
Compliance liability; team bandw…
CPO
Owns product roadmap
Resistant (has competing priorit…
Product strategy clarity
Other roadmap items deprioritized
VP Sales
Delivers the win rate recovery
Strongly supportive
Faster the better
Losing deals right now; needs th…
CFO
Controls capital
Neutral
Payback period <24 months; break…
What if win/loss shows payroll i…
CS Lead
Delivers customer success post-l…
Neutral
Clear launch plan + escalation path
Compliance errors will fall to them
BCG Consulting Framework · Apex HR · 2026-06-18
3 / 5

## Slide 4
Pre-Wire Sequence
Apex HR
1. **Week 1**: Win/loss analysis brief to CEO — establishes evidence base before any ask
2. **Week 2**: CTO technical feasibility read-out — confirms Check integration is viable
3. **Week 3**: CPO 1:1 — address roadmap concern; agree what gets deferred vs. defended
4. **Week 4**: CFO business case review — sensitivity model, break-even conversation
5. **Week 5**: Board pre-read (CEO + CFO present) — no surprises in the formal meeting
6. **Week 6**: Formal board approval
BCG Consulting Framework · Apex HR · 2026-06-18
4 / 5

## Slide 5
Objections and Responses
Apex HR
Objection
Response
"What if payroll isn't the real …
Win/loss analysis will confirm b…
"$800K is a lot for a partner in…
It breaks even at 15% win rate r…
"Why not APAC instead?"
APAC requires the same payroll i…
"Won't Rippling just match us?"
They already have payroll. We're…
BCG Consulting Framework · Apex HR · 2026-06-18
5 / 5