## Slide 1
BCG-STYLE
04 / EXECUTION
Transformation Roadmap — Prism Analytics
Prism Analytics
2026-06-18
Powered by The Consultant's Guide to Claude · 21 BCG-Style Skills

## Slide 2
EXECUTIVE SUMMARY
Target Outcome
By month 12 (June 2027), Prism Analytics will have: (1) launched the LLM Intelligence Interface to market with ≥6 referenceable design partners and a credible "AI-first compliance intelligence" positioning, (2) won 15–20 net-new logos in the Tier 1 bank and insurance segments, lifting ARR from $48M to ≥$55M, (3) stabilized NRR at ≥107% through LLM expansion upsell at renewal, (4) reduced burn to ≤$1.85M/mo extending runway to ≥18 months from month 12, and (5) maintained a live M&A parallel track with a prepared data room and ≥2 qualified buyer conversations completed. At the month 12 board review, Prism will make a binary decision: accelerate to Series D and replatform, or close a strategic transaction.
Prism Analytics
BCG Consulting Framework · Prism Analytics · 2026-06-18
2 / 6

## Slide 3
Workstreams
Prism Analytics
Workstream
Objective
Owner
Key Dependency
WS1 — LLM Intelligence Product
Compress LLM interface from 6 to…
CPO (accountable) + CTO (delivery)
Engineering squad reorg complete…
WS2 — AI-First Go-to-Market
Reposition Prism as "AI-first co…
VP Sales
Win/loss analysis complete by we…
WS3 — NRR Expansion Motion
Design and deploy LLM Intelligen…
VP Customer Success
LLM packaging approved by CPO an…
WS4 — Compliance Platform Depth
Release Basel IV phased implemen…
Head of Compliance Engineering
Compliance Engine Squad operatin…
WS5 — Financial Discipline and B…
Reduce monthly burn from $2.1M t…
CFO
Board approval for burn reductio…
WS6 — M&A Readiness and Strategi…
Maintain credible M&A parallel t…
CEO + CFO + financial advisor
Board alignment on exit price fl…
BCG Consulting Framework · Prism Analytics · 2026-06-18
3 / 6

## Slide 4
Roadmap
Prism Analytics
Phase
Timing
Major Actions
Milestones
Phase 1 — Mobilize
Months 1–2
Stand up 3 engineering squads (L…
M1: Squad reorg complete. M1: De…
Phase 2 — Deliver
Months 3–4
LLM interface development sprint…
M3: Design partner NPS ≥40 at mi…
Phase 3 — Launch and Sprint
Months 5–7
LLM Intelligence tier GA launch …
M5: LLM Intelligence tier live. …
Phase 4 — Scale and Decide
Months 8–12
Full new logo sprint execution; …
M9: ≥12 new logos won. M10: NRR …
BCG Consulting Framework · Prism Analytics · 2026-06-18
4 / 6

## Slide 5
First 90 Days
Prism Analytics
Week 1–2 — Alignment and commitment:
CEO announces AI-first strategy and 4-month LLM launch commitment at all-hands; names squad leads and PM for LLM Inte…
CTO publishes engineering reorg structure and 14-week sprint OKRs
CFO initiates discretionary spend audit; identifies $300K/mo reduction opportunities
VP Sales launches win/loss interview program (external consultant engaged)
Week 2–4 — Mobilization:
6 design partner accounts identified and NDA/beta agreements signed (VP CS and CPO own)
Insurance pod AE redeployments complete; territory assignments updated in CRM
Deal desk governance live in Salesforce; VP Sales briefs all AEs on new discount floors
Financial advisor engaged; preliminary buyer landscape scope agreed
Week 5–8 — Early delivery signals:
LLM Intelligence Squad mid-sprint review: design partner onboarding feedback incorporated
Win/loss analysis findings delivered; board briefed on real-time vs. LLM gap breakdown
First 3 Insurance prospects at active discovery stage
BCG Consulting Framework · Prism Analytics · 2026-06-18
5 / 6

## Slide 6
Governance
Prism Analytics
Cadence:
Weekly: LLM Squad sprint review (CPO + CTO + squad lead; 30 minutes; milestone RAG status)
Weekly: New logo sprint pipeline review (CEO + VP Sales; deal-level review of Tier 1 and Insurance pipeline)
Bi-weekly: Cross-workstream PMO sync (CEO, CPO, VP Sales, VP CS, CFO; 60 minutes; interdependency and risk log)
Monthly: Board update (CEO + CFO; ARR trajectory, burn, M&A track status, key risks)
Monthly: Design partner advisory council (CPO + 3 design partner CROs/CFOs; product feedback and reference story deve…
Escalation:
Any initiative more than 2 weeks behind milestone: CPO or workstream owner escalates to CEO within 48 hours
Burn exceeds $2.0M/mo for 2 consecutive months: CFO triggers emergency cost review with CEO and board within 5 busine…
Any inbound M&A inquiry from a strategic buyer: CEO notifies board chair within 24 hours; no engagement without board…
Success metrics (tracked monthly):
ARR (target: $55M by month 12)
New logos won in sprint window (target: 15 by month 10)
Win rate (target: ≥42% by month 6)
BCG Consulting Framework · Prism Analytics · 2026-06-18
6 / 6