## Slide 1
SOLUTION DELIVERY
RetailCo
Solution Blueprint
AI-Powered Customer Service Automation
Capability Map · Phased Delivery Plan · Integration Constraints
60% Deflection Target
3-Wave Delivery
SAP + Salesforce
June 2026

## Slide 2
Capability Map — Build / Buy / Partner Decision
AI customer service: full capability stack for Wave 1–3 delivery
Outcome
Capability
Component
Technology
Build / Buy
60% contact deflection
Intent classification
LLM classifier
Azure OpenAI GPT-4o
Buy
Conversation orchestration
LangGraph agent loop
LangGraph + Python 3.11
Build
Knowledge retrieval
RAG pipeline
Azure AI Search + GPT-4o
Build
Order status self-serve
Order data access
SAP OData integration
SAP S/4HANA OData API
Build (integration)
Returns initiation
Returns workflow
Returns API connector
Internal REST API v2
Build (integration)
Escalation to human
Handoff with context
CRM screen-pop
Salesforce Service Cloud CTI
Build (integration)
Quality & safety
Guardrails
Content safety + validation
Azure Content Safety + Pydantic
Buy
Buy = vendor platform
Build = internal / custom
Build (integration) = API wrapper
AI Consulting Toolkit · RetailCo · June 2026 · CONFIDENTIAL
1 / 3

## Slide 3
Phased Delivery — Gate-Controlled Wave Approach
Wave 1 = order status only · Wave 2 = returns + escalation · Wave 3 = optimise & scale
WAVE 1
Months 1–3
Order status self-serve
• Azure OpenAI + Content Safety provisioning
• RAG pipeline (4,200 SKUs + 800 FAQ articles)
• SAP OData integration — read-only order status
• Agent orchestration: classify → lookup → respond
• Guardrails + output validation layer
• Shadow mode UAT on 5% live traffic
GATE ≥85% accuracy on order status intents in UAT
WAVE 2
Months 4–6
Returns + escalation
• Returns API v2 integration
• Salesforce CTI screen-pop on escalation
• Expand intents: product Q&A, store locator, loyalty
• A/B test: AI-first vs IVR-first routing
• Target: 45% deflection
GATE Deflection ≥45% · CSAT ≥4.1/5.0
WAVE 3
Months 7–9
Optimise & scale
• Fine-tune classifier on 90 days of production data
• Redis cache layer for SAP (↓60% OData calls)
• Proactive order delay push notifications
• Scale to 100% inbound traffic
GATE Deflection ≥60% · Handle time for escalations ≤6 min
→
→
AI Consulting Toolkit · RetailCo · June 2026 · CONFIDENTIAL
2 / 3